## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | Function/Screen | Feature | Level* | Function/Screen Details | Planned | Status
| Login (e-mail, Google, two-factor) | Common | Complex | About 10 API endpoints of module: auth |  | Done
| Forgot / Reset Password | Common | Complex | About 10 API endpoints of module: auth |  | Done
| Change Password | Common | Complex | About 10 API endpoints of module: auth |  | Done
| Profile & Settings | Common | Complex | About 10 API endpoints of module: auth + users |  | Done
| Notifications | Common | Medium | About 4 API endpoints of module: notifications |  | Done
| Action History | Common | Medium | About 4 API endpoints of module: history |  | Done
| Dashboard Overview | Orders | Medium | Packing report + packaging-savings APIs (modules packing, packaging-materials); revenue-by-channel, finance and staff widgets still use sample data (no back-end aggregate API) | Iteration 3 | Doing
| Omnichannel Orders / Order Detail | Orders | Medium | About 4 API endpoints of module: orders |  | Done
| Groups & Express | Orders | Complex | About 15 API endpoints of module: order-groups |  | Done
| Order Sync Settings | Orders | Simple | About 3 API endpoints of module: order-sync-settings |  | Done
| Marketplace Connections | Marketplace | Medium | About 4 API endpoints of module: marketplace-integration |  | Done
| Warehouse Picking | Warehouse | Complex | About 15 API endpoints of module: order-groups (picking part) |  | Done
| Warehouse Inventory | Warehouse | Complex | About 39 API endpoints of module: warehouse |  | Done
| Admin Warehouse (structure, SKUs, mappings) | Warehouse | Complex | About 64 API endpoints of module: master-skus + categories + warehouse |  | Done
| Product Master (packaging profile) | Warehouse | Medium | About 5 API endpoints of module: product-master |  | Done
| Packing Station | Packing | Complex | About 29 API endpoints of module: packing-plan |  | Done
| Admin Packing Plans | Packing | Complex | About 29 API endpoints of module: packing-plan |  | Done
| Packaging Rules / Materials | Packing | Complex | About 26 API endpoints of module: packaging-materials + packaging |  | Done
| Shipping & Fulfillment | Shipping | Complex | About 27 API endpoints of module: shipments + shipping |  | Done
| Returns | Returns | Complex | About 12 API endpoints of module: returns |  | Done
| Staff Directory / Admin Roles | Admin | Complex | About 12 API endpoints of module: users + staff-assignment |  | Done
| AURELLE Home / Shop / Product Detail | AURELLE | Complex | About 19 API endpoints of module: storefront |  | Done
| AURELLE Cart / Checkout | AURELLE | Complex | About 19 API endpoints of module: storefront |  | Done
| AURELLE My Orders / Order Detail | AURELLE | Complex | About 19 API endpoints of module: storefront |  | Done
| AURELLE My Returns / Return Detail | AURELLE | Complex | About 19 API endpoints of module: storefront |  | Done
| AURELLE Customer Login / Register | AURELLE | Medium | About 4 API endpoints of module: storefront customer-auth |  | Done
| AURELLE Web Admin (Products, Categories) | AURELLE | Complex | About 15 API endpoints of module: storefront-admin |  | Done
| AURELLE Developer Portal | AURELLE | Simple | About 3 API endpoints of module: storefront-admin-auth / developer |  | Done
| Mobile App (picking / packing scan, shipment tracking, push notifications) | Mobile | Complex | Not implemented in this release; scanning is done on the web portal (Warehouse Picking, Packing Station). Planned Flutter app, Report 2 WBS 4.2 | Iteration 3 | Pending
(*) You can rate the functions' complexity based on the number of fields on the screens or the number of transactions in the function, with the details as below
| simple | <=7 fields | <=3 transactions
| medium | <=15 fields | <= 7 transactions
| complex | >15 fields | > 7 transactions
In which:
fields: screen components or database table fields
transactions: action buttons, user or database transactions
Note: Level is estimated from the number of API endpoints (transactions) of the module behind each screen, so screens that share a large module appear as Complex. Status 'Done' = implemented in the repository, 'Doing' = partly implemented, 'Pending' = not started; Planned (iteration) is filled only for unfinished items.

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
| Tiki and TikTok Shop adapter files exist in the code but are not registered; shops of these platforms cannot be connected and their orders are not processed. | Out of scope for this release (partner API access constraints, see BM03 #1). | Medium | Thuận | 25/10/2026 |  | Open | BM03 #1; Design Brief 1.2
| Lazada is read-only: order status changes are not written back to Lazada (only AURELLE gets write-back). | Lazada customers do not see OptiPack status changes. | Medium | Thuận | 25/10/2026 |  | Open | Design Brief 1.2
| No staging environment is declared; only local, Docker Compose and Kubernetes manifests exist (docs/DEPLOYMENT.md). | Review 2 requires demos on a declared staging environment. | High | Thuận | 25/10/2026 |  | Open | Design Brief R1 / G3 – before the Review 2 demo
| Collection packaging_recommendations is listed in the schema but no longer used by the current packing flow. | Entity in ERD / database without active code; may be flagged by the self-review. | Low | Thi | 25/10/2026 |  | Open | Design Brief G5 – due 20/11/2026
| Only GHN is integrated as a live carrier; other carriers are mock or manual. | Shipping depends on one carrier API. | Low | Thuận | 25/10/2026 |  | Open | Design Brief 1.2
| Mobile app (registration 3.2, Report 1 FE-06) is not implemented; planned for Iteration 3. | Picking and packing scanning is available only on the web portal. | Medium | Việt | 25/10/2026 |  | Open | Design Brief G1 – due 20/11/2026 (Iteration 3)
| Home dashboard widgets (revenue by channel, finance, staff) use sample data; the back end has no aggregate API for them. | Store Owner cannot rely on these widgets; real figures are in packing reports and action history. | Medium | Thuận | 25/10/2026 |  | Open | Design Brief G2 – due 20/11/2026
| Automated back-end tests use mocked database models; there is no end-to-end test against a real MongoDB replica set. | Transaction and index behaviour is not verified automatically end to end. | Medium | Thi | 25/10/2026 |  | Open | Design Brief G4 – due 04/12/2026

## Defects
PROJECT DEFECTS
Feature | Function/Screen | Tester | Defect Description | Assign To | Status | Notes
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## Q&A
PROJECT Q&A
Date | Question | By | Priority | Status | Note (answer, other notes)
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open
|  |  | Medium | Open